## TestPlan ScreenReader
Test Planner and Tracker |  |  | ProjectName
Remove sample items before submitting this.
Test No. ID | Trace to User Story ID and Name | Pre-conditions | Test Description (steps) | Expected Outcome | Sprint 1Outcome | Sprint 2 Outcome | Sprint 3 Outcome | notes for outcome(code yellow)
1 | R1 – Pet Profile: create and save basic profile | App installed; user is on Home screen; no pets saved yet. | 1. Tap 'Add Pet'. 2. Enter name, species, and age. 3. Tap 'Save'. 4. Return to Home screen. | New pet profile appears correctly with all details visible.
2 | R1 – Pet Profile: add and display pet photo | At least one pet exists without a photo. | 1. Open existing pet profile. 2. Tap 'Add Photo'. 3. Select camera or gallery. 4. Save. | Photo displays correctly and persists after restart.
3 | R1 – Pet Profile: edit existing pet profile | At least one pet profile already exists. | 1. Open existing pet. 2. Change pet details. 3. Tap 'Save'. 4. Reopen to verify changes. | Edited details are saved correctly and displayed properly.
4 | R2 – Owner & Emergency Contact Info: save and validate inputs | App installed; user on Settings/Contacts screen. | 1. Open 'Owner & Emergency Contacts'. 2. Enter valid data. 3. Tap 'Save'. | Owner and contact info save successfully and display correctly.
5 | R2 – Owner & Emergency Contact Info: input validation messages | Contacts screen opened; required fields empty. | 1. Leave phone/email blank. 2. Tap 'Save'. 3. Observe warning message. | Validation message appears clearly for missing required fields. |  |  |  | Validation messages appear but layout polish and multi-field check pending.
6 | R3 – Missing Pet Alert: generate alert text and preview | At least one complete pet profile exists with photo and contact info. | 1. Open a pet profile. 2. Tap 'Missing Alert'. 3. Confirm alert generation. | Alert text generated accurately with pet and owner details. |  |  |  | Alert text generation complete; formatting and image embedding under test.
7 | R3 – Missing Pet Alert: share via email and social media | Missing Pet Alert already generated. | 1. Tap 'Share via Email'. 2. Choose an app. 3. Review email draft. | Pre-filled email with pet details and photo ready to send. |  |  |  | Email share functional; direct social-media integration next sprint.
8 | R4 – Regular Update Prompts: periodic reminders | At least one pet exists with outdated info. | 1. Launch app after reminder period. 2. Observe notification. | User sees polite reminder to update pet info/photo.
9 | R5 – Recommendations Section: view and scroll | App installed; Recommendations accessible from menu. | 1. Open 'Recommendations'. 2. Scroll through. 3. Tap one item. | Recommendations display correctly and load smoothly.
10 | R6 – Toxic Food Infographics: open and navigate | App installed; Infographics screen accessible. | 1. Open 'Toxic Foods for Pets'. 2. Scroll and tap any card. | Infographics are visible, readable, and stable. |  |  |  | Infographics display; category filter and image scaling pending
11 | Overall Sprint 2 Status: 70% features operational (core modules stable and improving visually).
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29