## TestPlan ScreenReader
Test Planner and Tracker |  |  | ProjectName
Remove sample items before submitting this.
Test No. ID | Trace to User Story ID and Name | Pre-conditions | Test Description (steps) | Expected Outcome | Sprint 1Outcome | Sprint 2 Outcome | Sprint 3 Outcome | Sprint 4 Outcome | Sprint 5 Outcome | notes for outcome(code yellow)
1 | R1 – Pet Profile: create and save basic profile | App installed; user is on Home screen; no pets saved yet. | 1. Tap 'Add Pet'. 2. Enter name, species, and age. 3. Tap 'Save'. 4. Return to Home screen. | New pet profile appears correctly with all details visible. | [5 empty] | Now stores pet profile in Firebase Firestore instead of local storage. Verified successful cloud persistence and retrieval after app restart.
2 | R1 – Pet Profile: add and display pet photo | At least one pet exists without a photo. | 1. Open existing pet profile. 2. Tap 'Add Photo'. 3. Select camera or gallery. 4. Save. | Photo displays correctly and persists after restart. | [5 empty] | Photo successfully uploads to Firebase Storage and persists across sessions and devices.
3 | R1 – Pet Profile: edit existing pet profile | At least one pet profile already exists. | 1. Open existing pet. 2. Change pet details. 3. Tap 'Save'. 4. Reopen to verify changes. | Edited details are saved correctly and displayed properly. | [5 empty] | Firestore document updates correctly. Changes reflected immediately in UI and persist across devices.
4 | R2 – Owner & Emergency Contact Info: save and validate inputs | App installed; user on Settings/Contacts screen. | 1. Open 'Owner & Emergency Contacts'. 2. Enter valid data. 3. Tap 'Save'. | Owner and contact info save successfully and display correctly. | [5 empty] | Validation works
5 | R2 – Owner & Emergency Contact Info: input validation messages | Contacts screen opened; required fields empty. | 1. Leave phone/email blank. 2. Tap 'Save'. 3. Observe warning message. | Validation message appears clearly for missing required fields. | [5 empty] | Validation messages appear
6 | R3 – Missing Pet Alert: generate alert text and preview | At least one complete pet profile exists with photo and contact info. | 1. Open a pet profile. 2. Tap 'Missing Alert'. 3. Confirm alert generation. | Alert text generated accurately with pet and owner details. | [5 empty] | Alert text generation complete; formatting and image embedding under test.
7 | R3 – Missing Pet Alert: share via email and social media | Missing Pet Alert already generated. | 1. Tap 'Share via Email'. 2. Choose an app. 3. Review email draft. | Pre-filled email with pet details and photo ready to send. | [5 empty] | Email share functional; direct social-media integration next sprint.
8 | R4 – Regular Update Prompts: periodic reminders | At least one pet exists with outdated info. | 1. Launch app after reminder period. 2. Observe notification. | User sees polite reminder to update pet info/photo.
9 | R5 – Recommendations Section: view and scroll | App installed; Recommendations accessible from menu. | 1. Open 'Recommendations'. 2. Scroll through. 3. Tap one item. | Recommendations display correctly and load smoothly.
10 | R6 – Toxic Food Infographics: open and navigate | App installed; Infographics screen accessible. | 1. Open 'Toxic Foods for Pets'. 2. Scroll and tap any card. | Infographics are visible, readable, and stable. | [5 empty] | Infographics display works
11 | R7 – Pet Profile: Store pet data in cloud (Firestore migration) | User logged in with Firebase account. | 1. Add new pet .2. Close app completely. 3.Reopen app. 4. Login again. | Pet data loads from Firestore and displays correctly. | [5 empty] | Successfully loads pet data from Firebase Firestore.
12 | R8 – Pet Profile: Cloud synchronization | Two devices logged in with same account. | 1. Add pet on Device A. 2. Login on Device B. 3. Refresh pet list. | Pet appears on both devices. | [5 empty] | Real-time data consistency confirmed.
13 | R8 – Reminders: create reminder | User logged in; reminders feature accessible. | 1. Open Reminders screen 2.Tap Add Reminder 3.Enter title, date, time 4.Save reminder | Reminder appears in reminder list with correct date and time. | [5 empty] | Reminder saved successfully using local storage (SharedPreferences).
14 | R8 – Reminders: edit reminder | At least one reminder exists. | 1. Open existing reminder 2. Edit title or time 3. Save changes | Updated reminder details display correctly. | [5 empty] | Reminder updates correctly and persists after app restart.
15 | R8 – Reminders: mark reminder complete | Reminder exists. | 1. Open reminders list 2. Tap Mark Complete | Reminder status changes to completed. | [5 empty] | Completion state stored locally and UI updates correctly.
16 | R9 – Missing Alert: contact selection | At least one saved contact exists. | 1. Open Create Missing Alert 2. Tap Select Contact 3. Choose saved contact | Contact name and phone autofill. | [5 empty] | Contacts module successfully integrates with Missing Alert form.
17 | R7 – Toxic Food Information: search and display | Tips & Toxic Foods screen accessible. | 1. Open Toxic Foods page 2. Use search bar 3. Select a food item | Food safety information displays correctly. | [5 empty] | Search and category filtering working correctly.
18 | 95% complete – Firebase Auth + Firestore storage + Login/Signup + Missing Alerts + Pet Profiles + Contacts + Reminders + Toxic Foods completed. Notifications and advanced integrations planned for next sprint.